YOUR COMPANY NAME

Business Project Proposal

Warehouse Automation & Inventory Tracking System

| Prepared for | Greenfield Distribution Ltd. |
| --- | --- |
| Prepared by | Your Name, Business Development Manager |
| Date | November 2, 2026 |
| Proposal reference | BP-2026-031 |
| Valid until | December 31, 2026 |

CONFIDENTIAL — This proposal contains pricing and information intended only for the named recipient.

EXECUTIVE SUMMARY

Greenfield Distribution handles more than 4,000 orders a week from its main warehouse. Manual stock counts and paper pick lists cause picking errors of about 3% and frequent stock-outs. We propose a barcode-based inventory tracking system with handheld scanners, real-time stock dashboards and automated reorder alerts. The project will take 14 weeks and is expected to pay for itself within 18 months.

BACKGROUND & BUSINESS NEED

Order volume has grown 35% in two years, but warehouse processes have not changed. Each picking error costs an average of $42 in returns, reshipping and staff time, or roughly $260,000 a year. Leadership has set a goal of 99.5% order accuracy by the end of 2027.

PROPOSED SOLUTION

•  Barcode labeling of all 6,500 storage locations and SKUs

•  20 rugged handheld scanners connected to a cloud inventory platform

•  Real-time dashboards for stock levels, picking speed and accuracy

•  Automated reorder alerts integrated with the current ERP system

•  On-site training for 45 warehouse staff and 6 supervisors

GOALS & SUCCESS MEASURES

| Goal | Current | Target | Measured by |
| --- | --- | --- | --- |
| Order picking accuracy | 97.0% | 99.5% | Weekly QA audits |
| Stock-outs per month | 28 | 5 or fewer | ERP reports |
| Time to complete stock count | 3 days | 4 hours | Cycle count logs |
| Average pick time per order | 11 min | 7 min | Scanner data |

PROJECT TIMELINE

| Phase | Duration | Milestone |
| --- | --- | --- |
| 1. Site survey and system design | Weeks 1–3 | Design sign-off |
| 2. Labeling and hardware installation | Weeks 4–7 | All locations labeled |
| 3. Software setup and ERP integration | Weeks 6–10 | Integration tested |
| 4. Training and pilot | Weeks 11–12 | Pilot accuracy above 99% |
| 5. Full go-live and handover | Weeks 13–14 | Project closed |

INVESTMENT

| Item | Qty | Unit Price | Amount |
| --- | --- | --- | --- |
| Handheld barcode scanners | 20 | $1,150 | $23,000 |
| Inventory software license (year 1) | 1 | $14,400 | $14,400 |
| Labels, printers and installation | 1 | $9,800 | $9,800 |
| ERP integration and configuration | 1 | $12,500 | $12,500 |
| Training and go-live support | 1 | $5,300 | $5,300 |
| Total Investment |  |  | $65,000 |

Payment terms: 40% on signing, 40% at hardware installation, 20% at go-live.

WHY CHOOSE US

•  12 years delivering warehouse and logistics systems

•  More than 80 successful installations across the region

•  Dedicated project manager and 12 months of free support

ACCEPTANCE

By signing below, both parties agree to the scope, timeline and investment described in this proposal.

| Client Name, Title / Date | Your Name, Title / Date |
| --- | --- |