## Timeline
Project Proposal Timeline
Enter each task with start and end dates. The Gantt bars and week headers update automatically from the project start date.
Project Start | 2026-11-16 |  |  |  |  | Project | Customer Portal Redesign
Project Lead | Your Name |  |  |  |  | Finish
Phase | Task | Owner | Start | End | Days
Discovery | Kick-off and stakeholder interviews | PM | 2026-11-16 | 2026-11-25
Discovery | Requirements sign-off | Sponsor | 2026-11-26 | 2026-11-30
Design | Wireframes and prototype | UX | 2026-12-01 | 2026-12-16
Design | Usability testing | UX | 2026-12-17 | 2026-12-24
Build | Front-end development | Dev | 2026-12-25 | 2027-01-21
Build | Integration and QA testing | QA | 2027-01-15 | 2027-01-28
Launch | Staff training | PM | 2027-01-25 | 2027-01-31
Launch | Go-live and support | Team | 2027-02-01 | 2027-02-07
Total days