RESEARCH PROJECT PROPOSAL Effects of Remote Work on Employee Well-Being Principal Investigator: Your Name • Department / Institution • November 2026

| Principal Investigator | Your Name, Ph.D. | Duration | 12 months |
| --- | --- | --- | --- |
| Co-Investigators | Name, Name | Requested Budget | $38,500 |
| Funding Body | Grant / Program Name | Submission Date | November 30, 2026 |

1. ABSTRACT

This study will examine how remote and hybrid work arrangements affect employee well-being, productivity and sense of belonging, using a mixed-methods design across five mid-sized organizations.

2. BACKGROUND AND RATIONALE

Remote work has grown rapidly since 2020, yet evidence on its long-term effects on well-being is mixed. Organizations need practical guidance on which arrangements support healthy, engaged teams.

3. RESEARCH QUESTIONS

•  How do remote, hybrid and on-site employees differ in reported well-being?

•  Which workplace practices are linked to higher belonging for remote staff?

•  How do these outcomes change over a 12-month period?

4. METHODOLOGY

| Component | Approach |
| --- | --- |
| Design | Mixed methods: longitudinal survey and interviews |
| Participants | 600 employees from 5 organizations |
| Data collection | Surveys at months 0, 6 and 12; 30 interviews |
| Analysis | Regression models and thematic analysis |
| Ethics | IRB approval, informed consent, anonymized data |

5. TIMELINE AND BUDGET

| Phase | Months | Budget |
| --- | --- | --- |
| Ethics approval and setup | 1 – 2 | $3,000 |
| Baseline survey and interviews | 3 – 5 | $12,500 |
| Follow-up data collection | 6 – 10 | $14,000 |
| Analysis and reporting | 11 – 12 | $9,000 |

6. EXPECTED OUTCOMES

A peer-reviewed article, a practical guide for HR leaders and a public summary of findings shared with all participating organizations.

| Principal Investigator / Date | Department Head / Date |
| --- | --- |