PROJECT PROPOSAL Customer Portal Redesign Prepared by: Your Name, Project Lead • Your Company Name • November 2, 2026

| Project Name | Customer Portal Redesign | Proposal Date | November 2, 2026 |
| --- | --- | --- | --- |
| Prepared For | Operations Leadership Team | Proposal No. | PP-2026-014 |
| Project Sponsor | Maria Lopez, COO | Estimated Budget | $48,500 |

1. PROJECT SUMMARY

Our current customer portal is slow, hard to navigate on mobile and generates around 300 support calls a month. This project will redesign the portal so customers can track orders, download invoices and update their details without calling us.

2. PROBLEM STATEMENT

Customers struggle to find order status and billing information. Mobile users (62% of visits) abandon the portal twice as often as desktop users, and the support team spends roughly 25 hours a week answering questions the portal should answer.

3. OBJECTIVES

•  Reduce portal-related support calls by 40% within six months of launch

•  Achieve a mobile task completion rate of 90% or higher

•  Launch the new portal by March 31, 2027

4. SCOPE & DELIVERABLES

| In scope • User research and UX design • Responsive front-end build • Order tracking and invoice pages • Staff training and launch support | Out of scope • Changes to the billing system • Native iOS / Android apps • Data migration of pre-2020 orders |
| --- | --- |

5. TIMELINE

| Phase | Key Activities | Start | End |
| --- | --- | --- | --- |
| Discovery | Interviews, analytics review, requirements | Nov 16, 2026 | Dec 11, 2026 |
| Design | Wireframes, prototype, usability testing | Dec 14, 2026 | Jan 29, 2027 |
| Build | Development, integration, QA | Feb 1, 2027 | Mar 19, 2027 |
| Launch | Training, go-live, post-launch review | Mar 22, 2027 | Mar 31, 2027 |

6. BUDGET & RESOURCES

| Item | Cost |
| --- | --- |
| UX research and design (120 hrs) | $12,000 |
| Development and testing (260 hrs) | $28,600 |
| Hosting, tools and licenses | $3,400 |
| Contingency (10%) | $4,500 |
| Total | $48,500 |

7. APPROVAL

| Project Sponsor / Date | Project Lead / Date |
| --- | --- |